heyyERP for V-Rub Suspensions

ERP Development Plan, Architecture and System Design

Prepared for: HeyyBot engineering team

Date: 23 Oct 2026   |   Version: 1.1 draft

Source inputs: BRD v1.0 draft (22 Oct 2026) and clickable prototype v4 (state key heyyerp-vrub-v4).

Status: planning document. Effort figures are the author’s estimates and should be re-baselined after BRD sign-off.

Contents

1. Purpose and summary

1.1 Where the prototype stands

1.2 Effort and timeline at a glance

2. Target architecture

2.1 Principles

2.2 Logical layers

2.3 Deployment view

2.4 Production sizing (25–50 users at go-live)

3. System design

3.1 Module map and dependencies

3.2 Core data model

3.3 Approval and workflow engine

3.4 Inventory, lots and valuation

3.5 Production routes and compound batches

3.6 Finance, period lock and GST

3.7 Schedule import, labels and traceability

3.8 API design

3.9 Domain events (outbox pattern)

3.10 Security design

3.11 Integrations

3.12 Non-functional targets

4. Development plan

4.1 Phase overview

4.2 Phase 1: Foundation and platform core (~45 days)

4.3 Phases 2–7: scope and exit gates

4.4 Effort by work package

4.5 Team and roles

4.6 Timeline and day-wise schedule

5. Environments, CI/CD and testing

5.1 Environments

5.2 Pipeline

5.3 Test strategy

6. Data migration and rollout

7. Risks and mitigations

8. Open decisions

# 1. Purpose and summary

V-Rub Suspensions makes anti-vibration rubber and metal-bonded parts for OEMs across three plants with separate GSTINs. Operations run today on spreadsheets, an accounting package and paper travellers. heyyERP replaces them with one cloud system of record from vendor approval to dispatch. This document sets out how to build it: the target architecture, the system design of the hard parts, and a phase-by-phase development plan.

## 1.1 Where the prototype stands

| Area | Alignment | Comment |
| --- | --- | --- |
| Module screens (sales, procurement, inventory, quality, maintenance, HR) | ~90% | Every BRD tab exists; action-to-permission map matches. |
| Production routes, compound batches, FEFO / FIFO, QA gates | ~95% | Strongest part; rules are ready to port. |
| Approval engine and admin screens | ~85% | Missing delegation, e-mail / WhatsApp approval, atomic decisions. |
| Finance and GST | ~70% | Screens exist; IRN / e-way bill are mocked. |
| Auth and security | ~35% | Browser-only checks; no SSO, PIN, MFA, RLS. |
| Integrations | ~15% | Simulated or paste-in. |
| AI and OCR | ~25% | UI and prompts only. |
| NFRs, migration, infra, CI/CD, multi-tenancy | 0% | Not applicable to a client-only prototype. |

Overall the prototype covers about 85–90% of the behaviour and UX specification but only about 12–15% of the real engineering work. The BRD instructs the team to port the prototype’s rules, not its architecture.

## 1.2 Effort and timeline at a glance

| Team | Effort | Elapsed time |
| --- | --- | --- |
| 6 people (recommended) | ~760 person-days incl. 15% contingency | ~34 weeks (about 8 months) including UAT and cut-over |
| 8 people | ~760 person-days | ~28 weeks, with phases 3–6 overlapping |
| 3–4 people | ~760 person-days | 10–12 months |

Pure engineering capacity for 760 person-days with six people is about 25 weeks; the remaining weeks are dependency waits, UAT and the month-start cut-over. The BRD’s 14-week go-live is not achievable from scratch. The BRD itself flags the gap between its 14-week client plan and the PRD’s 28-week product build (BRD section 10.4). Section 4.6 gives the day-wise schedule.

# 2. Target architecture

## 2.1 Principles

- Modular monolith. One deployable API, with modules as isolated Python packages. Split into services only when a module proves it needs it.

- Session-based auth. Authentication uses Better Auth with secure session cookies. There are no JWTs; the API validates the session on every request.

- Multi-tenant from day one. Every row carries tenant_id with Postgres row-level security. V-Rub is tenant 1; the next customer needs no rewrite.

- Strict module boundaries. Modules call each other through in-process service interfaces and domain events, never by reading each other’s tables.

- Business rules as a pure library. FEFO, FIFO allocation, batch status, rule matching and period lock live in packages/domain as pure, unit-tested functions.

- Configuration over code. Every business setting and approval rule is data. Changing them is an admin action, not a release.

- Server-side security. The UI check is convenience only. Every endpoint declares a permission and the server enforces it.

## 2.2 Logical layers

| Layer | Technology | Responsibility |
| --- | --- | --- |
| Web app | React 18, TypeScript, Vite, TanStack Query, React Router; PWA | All screens, role-aware navigation, offline-tolerant shop-floor views, barcode scanning |
| Edge | Azure Front Door + WAF, CDN | TLS, WAF rules, static assets, optional India geo-restriction |
| Auth | Better Auth (TypeScript, Node) with the Postgres adapter, in its own small service | Sign-in, sessions, Microsoft / Google SSO, two-factor, OTP, user admin |
| API | FastAPI (async), Pydantic v2, SQLAlchemy 2, Alembic | REST /api/v1, OpenAPI, session validation, permission guard, audit middleware |
| Real-time | WebSocket gateway on FastAPI + Redis pub/sub | Approval inbox counts, “updated by” toasts, presence |
| Domain modules | sales, procurement, inventory, production, quality, maintenance, finance, gst, hr, workflow, admin, ai | Business rules ported from the prototype |
| Async workers | Celery or Dramatiq on Azure Service Bus; scheduler | Schedule import, OCR, GSP calls, reminders, nightly MRP, report export |
| Data | PostgreSQL 16 Flexible Server (zone-redundant HA), Redis, Blob Storage | Transactions, sessions and locks, documents and labels |
| AI | LLM gateway (Azure OpenAI + Anthropic Claude), Azure AI Document Intelligence | Copilot, agents, bill / delivery-challan / customer-PO OCR |
| Integrations | One adapter module with retry and dead-letter | GSP, mailbox, WhatsApp, bank file, accounting export, Zebra printers |

## 2.3 Deployment view

Users (browser / tablet / phone)

-> Azure Front Door + WAF + CDN

-> Container Apps: api (2-6) | auth (2) | ws-gateway (2) | worker (1-4)

-> PostgreSQL 16 (HA)   -> Redis   -> Service Bus   -> Blob (ZRS)

-> External: GSP | Microsoft Graph | WhatsApp API | LLM / OCR

Cross-cutting: Key Vault, Managed Identity, ACR, Azure Monitor / App Insights

DR: warm standby in Azure South India (geo-replica + geo-redundant backups)

Everything sits in Azure Central India inside one VNet with private endpoints. All infrastructure is Terraform; nothing is created by hand in the portal.

## 2.4 Production sizing (25–50 users at go-live)

| Resource | Sizing | Notes |
| --- | --- | --- |
| Container Apps | api 2–6 replicas (1 vCPU / 2 GiB); worker 1–4; ws-gateway 2; auth 2 (Better Auth) | KEDA scaling on HTTP and queue depth |
| PostgreSQL Flexible | D4ds_v5, 256 GB, zone-redundant HA | PITR 35 days; read replica for reports from phase 2 |
| Redis | Standard C1 | Sessions, rate limits, locks, pub/sub |
| Service Bus | Standard | Queues: imports, ocr, gsp, notify; topics for domain events |
| Blob Storage | Hot, ZRS, Cool after 90 days | Attachments, labels, exports; virus scan on upload |
| Front Door + WAF | Standard, OWASP rule set | Custom domain per tenant |

# 3. System design

## 3.1 Module map and dependencies

| Module | Owns | Depends on (via service interface / events) |
| --- | --- | --- |
| admin / security | Roles, permissions, settings, audit log; extends Better Auth users with role and plant scope | Better Auth service (foundation) |
| workflow | Approval rules, instances, actions, delegation | admin; document adapters from other modules |
| inventory | Items, lots, stock ledger, FIFO cost layers, counts, transfers | admin, workflow |
| procurement | Vendors, indents, POs, GRN, returns, bills match input | inventory, workflow, quality |
| quality | QA queue, inspections, NCR/8D, PPAP, SPC, calibration | inventory, production |
| production | Compounds, batches, routes, lots, shift entry, BOM, MRP | inventory, quality, workflow |
| sales | Customers, SOs, schedule import, dispatch, challans, invoices | inventory, production, gst |
| finance / gst | Chart of accounts, journals, AP / AR, periods, returns, TDS | Consumes events from all posting modules |
| maintenance | Machines, moulds, PM, breakdowns, assets, depreciation | inventory (spares), finance |
| hr / kaizen | Employees, leave, attendance, appraisal, kaizen | workflow |
| ai | Copilot context, agents, OCR orchestration | Read-only access through the permission layer |

## 3.2 Core data model

All tables carry tenant_id, created_at, created_by, updated_at and version (optimistic lock). Plant-specific tables also carry unit_id. Money is numeric(18,2); quantities are numeric(18,3).

| Domain | Key tables |
| --- | --- |
| Org and security | tenant, unit (gstin, state_code), store, department, app_user (role_id, unit_scope[], linked to the Better Auth user), role, permission, role_permission, role_module, audit_log (append-only). Better Auth owns user, session, account, verification and two_factor in an auth schema |
| Settings | business_setting (key, value jsonb, effective_from): grnTolPct, priceTolPct, requireIndent, negativeStock, issueRule, valuation, lockDay, prodLockExtraDays |
| Workflow | approval_rule, approval_rule_step, approval_instance, approval_action, delegation |
| Items and stock | item, lot (QA_HOLD / AVAILABLE / QUARANTINE / BLOCKED), stock_ledger, cost_layer, stock_count, stock_count_line |
| Procure-to-pay | vendor, indent(+line), purchase_order(+line, schedule), grn(+line), purchase_return, supplier_bill, bill_match |
| Order-to-cash | customer, price_list, sales_order(+line, schedule), schedule_import, dispatch, invoice, inter_unit_invoice, challan |
| Production | compound, compound_recipe_line, compound_batch, batch_weighing_line, route, route_stage, prod_lot, prod_lot_move, lot_consumption, shift_production, bom, work_order |
| Quality | qa_inspection (subject_type, result, params jsonb), ncr, ncr_step, calibration |
| Maintenance | machine, mould, pm_plan, pm_task, breakdown, spare_issue, fixed_asset, depreciation_run |
| Finance and GST | account, journal, journal_line, period, payment, payment_run, gst_return_data, tds_entry |
| HR | employee, leave_type, leave_request, leave_balance, attendance, appraisal, kaizen |

## 3.3 Approval and workflow engine

One generic engine routes eight document types: indent, PO, supplier bill, scrap sale, stock count, leave, kaizen and annual review. Rules are rows in approval_rule, so an admin changes routes without a release. A rule change applies only to documents submitted afterwards.

- findRule: Match the first rule where the document type and amount band fit.

- resolveSteps: Replace DEPT_HEAD with the role mapped from the document’s department; collapse consecutive duplicate roles.

- startAppr: Skip leading steps held by the requester’s own role; auto-approve if none remain.

- decide: Only the current-step role (or ADMIN, logged as override) may decide. Approve advances or finalises; reject finalises. The type adapter’s final hook applies the business effect.

- Extensibility: Each document type is registered with an adapter (pending condition, amount, department, title, final). New types need no engine change.

- Concurrency: A decision runs in one transaction using optimistic locking on step and version. A second decision on the same step returns “Already decided”.

### Default approval matrix (proposal, to be replaced by V-Rub sheet 3)

| Rule | Document | Band | Steps | SLA |
| --- | --- | --- | --- | --- |
| R-IND | Indent (BOM / consumable) | any | Dept head → Plant Head | 24 h |
| R-IND-CAP | Indent (capital) | up to 5 L / 5–25 L / above 25 L | Dept head → Plant Head (→ MD above 25 L) | 72 h |
| R-PO-1/2/3 | Purchase order | up to 5 L / 5–25 L / above 25 L | Purchase → Plant Head → MD (by band) | 24 h |
| R-BILL | Supplier invoice exception | any | Accounts | 48 h |
| R-SCRAP, R-COUNT | Scrap sale, count variance | any | Plant Head → Accounts | 48 h |
| R-LEAVE, R-KZ, R-REV | Leave, kaizen, review | any | Dept head (→ Plant Head / HR) | 120–168 h |

## 3.4 Inventory, lots and valuation

- Every receipt creates a lot with expiry = received date + item shelf life. Goods land in QA_HOLD until inspection accepts them.

- Issues follow FEFO: earliest expiry first, then oldest receipt. Expired lots are blocked. A shortfall blocks the whole issue.

- stock_ledger is append-only. Balances are derived from it. Valuation is FIFO through cost_layer rows created per receipt.

- No transaction may take a store / item / lot below zero. Enforced with SELECT ... FOR UPDATE on the lot rows and a CHECK constraint as a backstop.

- Every POST that moves stock or money takes an idempotency key, so retries cannot double-post.

- Inter-plant transfers raise an inter-unit invoice and e-way bill (RULE-14).

## 3.5 Production routes and compound batches

Routes are data (route and route_stage with an is_qa_gate flag). METAL runs machining, QA, phosphating, QA and painting. MOULD runs moulding, QA, packing and FG store. EXTR runs extrusion, joint moulding or flocking, QA and packing.

- Derived status. Compound batch status is never stored as truth. A view derives Weighed / Mixing, Maturing (age below minimum), Awaiting QA, Ready, Consumed (kg left = 0), Expired (age above maximum) or Rejected, from mixed_at, QA result and kg_left.

- Allocation. A moulding lot draws compound oldest-first across Ready batches and one metal lot that passed final metal QA. Each draw is a lot_consumption row, giving full traceability from RM lot to invoice.

- Gates. If Ready compound or metal is short, the lot cannot be created. QA stages require qa.approve; other stages require route.move.

- QA limits. Hardness outside the compound spec cannot be approved.

## 3.6 Finance, period lock and GST

- Auto-postings come from domain events (GRN, invoice, issue, production, payment) consumed by finance. Modules never write journals directly.

- Supplier bills use a 3-way match (PO, GRN, invoice) with 0% price tolerance. Quantity, rate or duplicate exceptions go to Accounts approval.

- A period guard runs on every posting service. Closed months refuse posting; production postings stay open until day 1 of the next month.

- E-invoice (IRN) and e-way bill go through a licensed GSP adapter with retry, dead-letter and a reconciliation view. V-Rub holds the GSP contract.

## 3.7 Schedule import, labels and traceability

- OEM schedules (.xlsx, .csv, or an e-mail attachment) are uploaded, parsed by a worker into schedule_import.parsed_rows, previewed with matches to customer / PO / part, then applied to create or update SO schedule lines. Target: 2,000 rows to preview in 15 s.

- Labels use Code 39. The API renders PDF or ZPL for Zebra printers through a print server at each plant. Batch labels add “usable from” and “use before”.

- A traceability index links RM lot → compound batch → metal lot → moulded lot → FG lot → invoice, rebuilt from lot_consumption and dispatch events.

## 3.8 API design

- REST, JSON, /api/v1/<module>/<resource>; OpenAPI is the contract; cursor pagination.

- Updates require If-Match with the row version. Stock and money POSTs require an idempotency key.

- Auth: Better Auth issues a signed, httpOnly, SameSite session cookie; there are no JWTs. FastAPI verifies the cookie with the shared secret and checks the session and user rows through a read-only Postgres role, so a deactivated user is refused on the next request. GET /me returns user, role, modules, permissions and unit scope.

- Key endpoints: /approvals, /approvals/{type}/{id}/decide, /procurement/*, /inventory/issues/plan then /inventory/issues, /production/batches and /production/lots, /quality/queue, /sales/schedule-imports, /sales/dispatches, /admin/*, /labels/{type}/{id}, /ai/ask.

## 3.9 Domain events (outbox pattern)

Writes append to an outbox table in the same transaction. A relay publishes to Service Bus topics. Consumers are notifications, the real-time gateway, finance auto-posting, the search index and the AI context cache.

| Event | Emitted by | Consumed by |
| --- | --- | --- |
| approval.step_pending / decided | workflow | Notifications (in-app, e-mail, WhatsApp), real-time inbox |
| grn.posted, qa.decided | procurement, quality | Inventory (QA hold to available), finance (GRN accrual) |
| stock.issued, lot.moved, lot.packed | inventory, production | Finance (WIP / FG valuation), traceability index |
| invoice.created | sales | GST adapter (IRN, e-way bill), finance (AR) |
| period.closed | finance | All posting services (guard cache refresh) |

## 3.10 Security design

| Area | Design |
| --- | --- |
| Identity | Better Auth: Microsoft Entra ID / Google SSO; email and password with Argon2id (custom hasher) and lockout after 5 failures; two-factor plugin for ADMIN, MD, ACCOUNTS; phone OTP or username + PIN on registered shop-floor terminals with 10-minute idle expiry; session revocation on deactivation |
| Authorisation | Every endpoint declares a permission; policy check server-side; unit scope applied in queries; Postgres RLS on tenant_id |
| Data | TLS 1.2+; encryption at rest; PAN and bank fields encrypted at column level |
| Audit | Append-only audit_log for sign-in, create, approve, reject, settings, rules and exports; retained 8 years |
| Application | OWASP ASVS L2; CSP, CSRF protection, Pydantic validation, file-type and antivirus checks on upload |
| AI | Copilot runs through the same permission layer; no tenant data used for training; prompts logged with PII redaction |
| Compliance | DPDP Act 2023; data resident in India |

## 3.11 Integrations

| System | Method | Phase |
| --- | --- | --- |
| GSP (e-invoice, e-way bill) | REST through licensed GSP; V-Rub holds the contract | 1 |
| Sales mailbox | Microsoft Graph / IMAP poller; attachments to schedule import | 1 |
| WhatsApp Business API | Template messages for approvals and alerts | 1 |
| Barcode printers | ZPL over network print server at each plant | 1 |
| Accounting package | Daily voucher export (XML / CSV) | 1, if retained |
| Bank | Payment file export; host-to-host later | 1 / 2 |
| Biometric attendance | Device vendor API or CSV pull | 2 |
| Machines / PLC, OEM portals, payroll | Out of scope for phase 1 | - |

## 3.12 Non-functional targets

| ID | Requirement | Target |
| --- | --- | --- |
| NFR-01 | Availability (monthly) | 99.5% |
| NFR-02 | API latency p95, reads / writes | 300 ms / 600 ms |
| NFR-03 | Page interactive on mid-range Android tablet over 4G | 3 s |
| NFR-04 | Concurrent users without degradation | 150 |
| NFR-05 | Approval event to approver’s inbox | 5 s |
| NFR-06 | Schedule import of 2,000 rows to preview | 15 s |
| NFR-07 | RPO / RTO | 15 min / 4 h |
| NFR-12 | No negative stock, no double approval under concurrency | Row locks |

# 4. Development plan

## 4.1 Phase overview

Phases are ordered by dependency so that each one ends in a working demo. Weeks assume a six-person team without AI assistance; see section 4.6 for the day-wise schedule.

| # | Phase | Weeks | Days | Outcome |
| --- | --- | --- | --- | --- |
| 1 | Foundation and platform core | 1–3 | ~45 | Login, RBAC, audit and CI/CD running in dev / qa |
| 2 | Workflow engine, masters, inventory ledger | 4–8 | ~85 | Approvals work; stock moves by lot with FEFO / FIFO, no negative stock |
| 3 | Procure-to-pay | 9–12 | ~70 | Indent → PO → GRN → QA → stock, plus returns and vendors |
| 4 | Production | 13–17 | ~75 | Routes, compound batches, lots, labels, shift entry, BOM / MRP |
| 5 | Order-to-cash, finance and GST | 18–23 | ~130 | Schedule import, dispatch, e-invoice, GL, 3-way match, period lock, GSTR |
| 6 | Maintenance, HR, kaizen, AI, integrations, reports | 24–28 | ~110 | Remaining modules, WhatsApp, mailbox, ZPL, OCR, copilot |
| 7 | Migration, hardening, UAT, go-live | 29–34 | ~100 | Data loads, performance and pen tests, training, cut-over |

Start Phase 5 early with a dedicated finance developer, because it is the largest and riskiest phase.

## 4.2 Phase 1: Foundation and platform core (~45 days)

Goal: a running, secure, empty ERP shell that every later module plugs into. No business screens yet.

| # | Task | Days | BRD reference |
| --- | --- | --- | --- |
| 1.1 | Monorepo: apps/web, apps/api (one package per module), apps/worker, packages/domain, infra/terraform, e2e | 3 | Section 9.3 |
| 1.2 | Terraform for Azure dev and qa: Container Apps, Postgres 16, Redis, Service Bus, Blob, Key Vault, ACR | 8 | Sections 9.1–9.2 |
| 1.3 | CI/CD on GitHub Actions: lint, mypy / tsc, tests, Alembic check, CodeQL, Trivy, deploy to dev (OIDC) | 5 | Section 9.3 |
| 1.4 | DB base: Alembic, tenant_id + RLS, unit_id, audit columns, version column, money / qty types | 4 | Section 8.2 |
| 1.5 | Org and security tables: tenant, unit, store, department, app_user, role, permission mappings | 3 | Section 3 |
| 1.6 | Better Auth service: email / password with Argon2id, secure session cookies, lockout, admin plugin for deactivate / reset, GET /me | 6 | FR-ADM-03 |
| 1.7 | FastAPI session validation and permission guard on every endpoint; seed 12 roles and the permission map from the prototype | 5 | BR-02, FR-ADM-04 |
| 1.8 | Append-only audit_log middleware | 3 | FR-ADM-05 |
| 1.9 | business_setting table with typed keys and admin GET / PUT | 3 | BR-11 |
| 1.10 | Admin API and UI: users CRUD, deactivate, reset password, role and plant scope | 4 | FR-ADM-01 |
| 1.11 | React shell: Vite, TanStack Query, router, role-aware nav, light / dark tokens, login, PWA basics | 5 | Section 8.1 |
| 1.12 | Test skeleton: pytest, Playwright role × screen sweep, 403 test for every endpoint | 3 | Section 10.3 |
| 1.13 | Seed fixtures ported from the prototype seed() | 2 | Section 9.2 |

Tasks sum to about 54 days; 1.3, 1.12 and 1.13 overlap with other work, which brings the phase to about 45.

### Exit gate (demo in dev)

- An admin signs in and creates a user with a role and plant scope; that user sees only permitted modules.

- A role without a permission gets 403; a deactivated user is signed out on the next request.

- Every sign-in, create and setting change appears in the audit log.

- A setting change takes effect without a redeploy.

- A merge to main auto-deploys to dev with all gates green.

### Deliberately out of Phase 1

Microsoft / Google SSO, two-factor, OTP and PIN (FR-ADM-06/07) are Better Auth plugins and are switched on in Phase 6. The approval engine and domain screens start in Phase 2. DR and production Terraform come in Phase 7.

## 4.3 Phases 2–7: scope and exit gates

### Phase 2: Workflow engine, masters, inventory ledger

- Scope: Approval engine with rule admin and inbox (FR-WF-01/02/05, FR-APR-01); item, vendor, customer masters; lot-level stock ledger, FIFO cost layers, FEFO issue plan, transfers, monthly count with approval; Code 39 labels; domain library with property tests.

- Exit gate: Two users approving the same step race safely; the last lot cannot be double-issued; a count variance posts only after approval.

### Phase 3: Procure-to-pay

- Scope: Indents (BOM / consumable / capital), POs from indents with value-band approval, vendor onboarding with GSTIN / PAN / bank checks, supplier schedules, GRN with +10% tolerance and QA hold, QA queue for GRN lots, purchase returns and debit notes, cash purchase, RFQ.

- Exit gate: Multi-user hand-off passes: stores raises indent, plant head approves, purchase creates PO, stores posts GRN, QA accepts, stock appears in store.

### Phase 4: Production

- Scope: Compound master and batch lifecycle with derived status, weighing, METAL / MOULD / EXTR routes with QA gates, FIFO consumption across batches and metal lots, packing to FG with labels, shift production entry, BOM, MRP to indents, OEE.

- Exit gate: A moulding lot cannot start without a matured, QA-approved batch and a painted insert lot; lot traceability reaches the compound batch and metal lot.

### Phase 5: Order-to-cash, finance and GST

- Scope: Sales orders, OEM schedule import (Excel / e-mail), dispatch with FIFO FG picking, invoice with IRN and e-way bill via GSP, inter-unit invoices, challans, scrap sales; chart of accounts, auto-postings, 3-way match, payment runs, AR ageing, period lock, consolidation, GSTR-1 / 3B, GSTR-2B reconciliation, TDS.

- Exit gate: A month can be closed; postings into a closed period are refused; the sandbox GSP returns an IRN for a test invoice; trial balance ties to subledgers.

### Phase 6: Maintenance, HR, kaizen, AI, integrations, reports

- Scope: Machine / mould master, PM, breakdowns, spares, fixed assets and depreciation; employees, leave, appraisal, kaizen; AI copilot and OCR agents; WhatsApp approvals, mailbox watcher, ZPL printing, bank file and accounting export; report library; SSO, OTP / PIN and two-factor through Better Auth plugins; delegation.

- Exit gate: All Must requirements demo-able in qa; a copilot answer respects the asker’s permissions; approval by WhatsApp link works once and only once.

### Phase 7: Migration, hardening, UAT, go-live

- Scope: Migration tooling and dry-run loads (masters, open POs / SOs, opening stock by lot, opening AR / AP); performance tests at 150 users; OWASP ZAP and external pen test; DR environment and failover runbook; UAT scripts; user training; cut-over at a month start with one week parallel run; 30-day hyper-care.

- Exit gate: Zero open Sev-1 / Sev-2; opening stock equals ledger and trial balance ties; first month-end closed in heyyERP.

## 4.4 Effort by work package

| Work package | Days | Phase |
| --- | --- | --- |
| Foundation: repo, Azure, CI/CD, auth, RBAC, RLS, audit, settings | 45 | 1 |
| Approval engine and admin screens | 30 | 2 |
| Inventory (lot ledger, FEFO / FIFO, counts, transfers, labels) | 55 | 2 |
| Procurement | 55 | 3 |
| Production routes, compound batches, manufacturing | 65 | 4 |
| Quality (queue, NCR / 8D, PPAP, SPC, calibration) | 35 | 3–4 |
| Sales, schedule import, dispatch, portal | 50 | 5 |
| Finance and GST | 80 | 5 |
| Maintenance and assets | 25 | 6 |
| HR and kaizen | 25 | 6 |
| AI copilot, agents, OCR | 30 | 6 |
| Integrations | 30 | 6 |
| Reports and dashboards | 20 | 6 |
| PWA, responsive layout, accessibility | 15 | 1–6 |
| Migration tooling and data loads | 25 | 7 |
| Test automation, performance, security and pen test | 45 | 1–7 |
| UAT support, training, hyper-care | 30 | 7 |
| Subtotal / +15% contingency / total | ~660 / ~100 / ~760 |  |

## 4.5 Team and roles

| Role | Count | Focus |
| --- | --- | --- |
| Backend engineers | 2–3 | Domain modules, workflow engine, ledger, integrations |
| Frontend engineers | 2–3 | React screens ported from the prototype, PWA, shop-floor views |
| DevOps / platform | 1 | Terraform, CI/CD, observability, DR |
| QA automation | 1 | Playwright suites, API contract tests, concurrency tests |
| Product owner / functional consultant | 1 (part-time) | Owns BRD, V-Rub sheets, UAT scripts |

## 4.6 Timeline and day-wise schedule

Assumptions: six-person team, five working days per week, working days numbered from kick-off (Day 1). Each phase ends on a fixed day with a demo against its exit gate.

| Phase | Working days | Weeks | Person-days | Completed on that day |
| --- | --- | --- | --- | --- |
| 1 | Day 1–15 | 1–3 | ~45 | Day 15: login, roles, audit and CI/CD live in dev |
| 2 | Day 16–40 | 4–8 | ~85 | Day 40: approvals and lot ledger demo; concurrency tests pass |
| 3 | Day 41–60 | 9–12 | ~70 | Day 60: indent → PO → GRN → QA → stock hand-off passes |
| 4 | Day 61–85 | 13–17 | ~75 | Day 85: batch → mature → QA → mould → pack traceable |
| 5 | Day 86–115 | 18–23 | ~130 | Day 115: test month closed; sandbox IRN issued |
| 6 | Day 116–140 | 24–28 | ~110 | Day 140: every Must requirement demo-able in qa |
| 7 | Day 141–170 | 29–34 | ~100 | Day 170: go-live; hyper-care runs the next 30 calendar days |

The phase view totals about 615 person-days. The remaining effort in the 660 subtotal (accessibility, test automation, performance) is spread across all phases. Day counts are working days; add public holidays and V-Rub’s shutdowns.

### Phase 1 day-by-day (Day 1–15)

| Day | Backend 1 | Backend 2 / DevOps | Frontend | QA |
| --- | --- | --- | --- | --- |
| 1 | Repo layout, FastAPI skeleton, Alembic init | Azure subscription, Terraform state, network | Vite + React + TS project, router | Test plan; pytest and Playwright setup |
| 2 | DB base: tenant_id, audit columns, version, money / qty types | Terraform: Postgres, Redis, Key Vault | App shell layout; design tokens from prototype | CI test jobs |
| 3 | Row-level security policies, tenant context middleware | Terraform: Container Apps, ACR, Service Bus, Blob | Login page, nav skeleton | Fixture loader skeleton |
| 4 | Better Auth service scaffold, Postgres adapter, auth schema | GitHub Actions: lint, type check, tests | Auth client, login form wired | Fixtures from prototype seed() |
| 5 | Email / password, Argon2id hasher, cookie config, lockout after 5 failures | OIDC to Azure; deploy-to-dev pipeline | Session handling, protected routes | Auth test cases |
| 6 | Admin plugin: deactivate, reset password | Alembic check, CodeQL, Trivy in PR pipeline | Role-aware nav from modules | Playwright login flow |
| 7 | FastAPI session validation, GET /me | Deploy auth service to dev | 403 and empty states | 403 test harness |
| 8 | Org tables: unit, store, department, role, permission | Deploy api + auth + web to dev; smoke tests | Admin users list screen | Role × screen sweep skeleton |
| 9 | Permission guard; seed 12 roles and permission map | business_setting table and API | Create / edit user form | 403 matrix generator |
| 10 | Plant-scope filter in queries | Settings admin endpoints | Role and plant pickers; deactivate, reset | Permission guard tests |
| 11 | Append-only audit_log middleware | Deploy qa environment | Settings screen | Audit tests |
| 12 | Audit hooks for sign-in / sign-out | App Insights, logs, health checks | PWA basics: manifest, service worker | Role sweep for all 12 roles |
| 13 | Session revocation on deactivation verified | Secrets in Key Vault; managed identity | Accessibility pass on shell and forms | Regression run on qa |
| 14 | Bug fixes from QA run | Runbook and README | Bug fixes | Re-test; gate checklist |
| 15 | Exit-gate demo and retrospective | Exit-gate demo | Exit-gate demo | Sign-off; Phase 2 backlog grooming |

Phases 2–7 get the same day-by-day breakdown at the start of each phase, once the previous phase’s actual velocity is known.

# 5. Environments, CI/CD and testing

## 5.1 Environments

| Env | Purpose | Data | Deploy trigger |
| --- | --- | --- | --- |
| dev | Developer integration | Seed fixtures from prototype | Every merge to main |
| qa | Automated and manual testing | Seed + generated volume | Nightly / on demand |
| uat | V-Rub key users | Migrated masters (masked where needed) | Release candidate tag |
| prod | Live | Live | Manual approval after UAT sign-off |
| dr | Warm standby, South India | Geo-replica | Terraform; failover runbook |

## 5.2 Pipeline

- Pull request: ruff, eslint, mypy, tsc, unit tests, Alembic migration check, CodeQL / Semgrep, Trivy.

- Merge to main: build and sign images, push to ACR, deploy to dev, run smoke and API contract tests.

- Release tag: deploy to qa then uat; run the full Playwright suite including role × screen and multi-user hand-offs.

- Production: manual approval, blue / green revision swap, expand-then-contract DB migrations, automatic rollback on failed health checks.

GitHub Actions uses OIDC federation to Azure; no long-lived cloud secrets in CI.

## 5.3 Test strategy

| Level | Scope | Tooling |
| --- | --- | --- |
| Unit | FEFO, fifoAlloc, batch status, rule matching, period lock, tolerances | pytest, Hypothesis property tests |
| API / contract | Every endpoint, including 403 for each role lacking the permission | pytest + schemathesis on OpenAPI |
| End-to-end | Role × screen sweep; hand-offs: indent → PO → GRN → QA → store; batch → mature → QA → mould → pack → dispatch | Playwright |
| Concurrency | Two users approving the same step; two issues on the last lot | Locust + targeted race tests |
| Performance | NFR-02 to NFR-06 at 150 users | k6 / Locust |
| Security | OWASP ZAP, dependency and container scans, pen test before go-live | ZAP, Trivy, external tester |
| UAT | Business scenarios per module signed by key users | UAT scripts |

# 6. Data migration and rollout

Go-live is planned 14 weeks after kick-off in the BRD, followed by 30 days of hyper-care. This document recommends re-baselining that date after the Phase 1 velocity is known. Cut-over happens at a month start so opening balances match a closed month in the old books, with a one-week parallel run on stores and dispatch.

| Object | Source | Validation |
| --- | --- | --- |
| Units, stores, GSTINs, departments | V-Rub sheet 1 | Admin review |
| Users and roles | V-Rub sheet 2 | Each user signs in during UAT |
| Items, HSN, UoM, shelf life, ROP / ROQ | Current item list | No duplicate codes; HSN valid |
| Compounds, recipes, BOMs, routes | Process sheets | Sample FG costed and approved |
| Vendors, customers, price lists | Accounting package | GSTIN and PAN validated |
| Open POs, open SOs, schedules | Spreadsheets | Line count and value tie-out |
| Opening stock by lot and store | Physical count at cut-over | Count = ledger; value = books |
| Opening AR / AP, trial balance | Accounting package | TB ties to last closed month |

Loads go through the same API validations as user entry (no direct SQL inserts), with a dry-run report before each load.

# 7. Risks and mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| V-Rub has not returned workflow sheets 1–6 and 8; 9 business-rule questions open | High | Settings and rules are data, so answers change configuration, not code. Escalate to MD / Plant Head with dated deadlines. |
| GSP not selected; sandbox access delayed | High | Build against an adapter interface with a mock; select GSP before Phase 5 starts. |
| Finance and GST is the largest module and least developed in the prototype | High | Dedicated finance developer; start in Phase 4; early accountant review of postings. |
| Concurrency defects (negative stock, double approval) | High | Row locks, idempotency keys, CHECK constraints, race tests in CI. |
| Month-start cut-over slips | Medium | UAT exit gate on Sev-1 / Sev-2; rehearse the load twice; agree a fallback month. |
| Scope drift from prototype-only pages (go-live, benchmark, integrations) | Medium | Treat the BRD as scope; keep these pages out of the build. |
| Better Auth (TypeScript) beside a Python API adds a second runtime and a session-sharing design | Medium | Keep it a small isolated service; spike session validation in week 1; fall back to FastAPI-native session auth if the spike fails. |
| Shop-floor adoption (tablets, scanners, PIN sign-in) | Medium | Early pilot at one plant; PWA with offline tolerance; on-site training. |

# 8. Open decisions

- Team size and composition (the schedule assumes six people).

- Azure subscription and tenant ready before Phase 1 task 1.2.

- Confirm Better Auth as a separate TypeScript service beside FastAPI, and validate session sharing in a Phase 1 spike.

- Confirm the BRD stack (FastAPI, React, PostgreSQL, Azure) or provide alternatives.

- Which platform modules already exist, to reconcile the 14-week client plan with the 28-week product plan.

- Select the GSP for e-invoice and e-way bill; V-Rub to hold the contract.

- Whether the existing accounting package stays as books of record (drives FR-FIN-08).

- Replace the default approval matrix with V-Rub’s sheet 3; decide cash purchase limit, minimum quotes and margin needing MD approval.

- Confirm real GSTINs, plant names and the store list.

- Number of login accounts at go-live (billing basis).